## Estimating template guidelines
Delete this sheet before submitting estimate
Start with "the Costs number" provided in the Business Case during Phase 0 …
Project Costs as defined in the Business Case template instructions are:
…. any costs related to completing this project including: development costs,
software costs, hardware costs, etc. as well as ongoing support costs.
As a starting point, apportion the cost dollars across the Phases of the project. (Tops Down estimate)
Further breakdown the phases of the project into a task/activity list for each phase.
Estimate the effort & costs for the project against the task/activity list (see the "effort" tab)
(Consider the following areas in estimating your software development (or upgrade) project :)
Development Effort - (time*rate) by resource type, by project phase, by task/activity
Hardware Costs
Software Costs
Networks
On-going support Costs
Admin costs (above typical overhead)
For increased accuracy, re-estimate the project using a bottoms up approach and reconcile the major differences
between the Top down and the Bottoms up estimates.(Whenever possible seek an independent validation of the
estimate before providing it to your Client.)
Document the risks assessed and assumptions made that support the estimate.
The various tabs in this workbook are intended as aids in estimating I.S. projects.
Please note … the various sample tables, and estimating checklists, used throughout the workbook are intended as
guidelines or examples for potential tables to be used for individual projects. In many cases, experienced
Project Managers will have far more sophisticated tables that will better serve the project. These should
definitely be substituted for the table in the workbook. Where the Project Manager does not have such an instrument,
the workbook tables might serve as a base for what is needed for the project being estimated.
The colors and markings in this workbook have the following meanings.
Green Cells = Calculated Numbers
Gray Cells = numbers or fields to be supplied by template user.
Project: Encompassing the totality of the undertaking. | Other colors/patterns have no meaning other than formatting
See the estimating Workbook presentation for information on how to use the estimating tabs.
Source: www.protrain-china.com

## (1) Resumo das estimativas
Luan Pimentel de Santana |  |  | SISTEMA DIEX / 1.0
Gestor de projetos |  |  | 2013-04-18
| Mão de obra | 1500
| Hardware | 700
| Software | 500
| Rede | 250
| Custos administrativos | 350
| Sub Total | 3300
| Risk | 170 |  | Fator de risco do projeto | 10%
| Change | 230 |  | Fator de mudança do projeto | 15%
| Total (incluindo riscos e mudanças) | 3700

## (2) Mão de obra
Total do esforço estimado |  |  | 150
Nome do projeto/número ______________ | [7 empty] | Gerente de projetos __________
Data __________
Atividade/Tarefa ID (#) |  | Atividade/Tarefa | Tipo do recurso | Quantidade do recurso (por tipo) * | Custo por hora | Horas necessárias | Estimativa sub-total | Observações
|  |  |  | 2 | 50 | 3 | 150
[6 empty] | Total | 150
|  | Resource type | estimated | not estimated * |  | Resource type estimate checklist:
IS Project Team
|  | Project Manager |  | X
|  | Project Leader |  | X
|  | Analyst |  | X
|  | Programmer |  | X
|  | Tester |  | X
|  | Documentation |  | X
|  | Third Party Prime (e.g. EPIC, Origin, BaaN) |  | X
|  | BaaN Core Program Interface Prime |  | X
|  | Integration Partners Core |  | X
|  | Integration Partner Non-Core |  | X
IS Support Functions
|  | New Product Introduction (NPI) Prime |  | X
|  | DBA |  | X
|  | Processing Services Prime |  | X
|  | Desktop Prime |  | X
|  | Networking Services Prime |  | X
|  | Vendor Management Prime |  | X
|  | Deployment Prime |  | X
|  | Captive Office Prime |  | X
|  | Functional Design Expert |  | X
|  | Detail Design Expert |  | X
IS Other
|  | Configuration Management Prime |  | X
|  | Client Manager |  | X
|  | Internal Audit |  | X
|  | Quality Assurance Prime |  | X
|  | Product Prime |  | X
|  | Program Office Prime |  | X
|  | Release Manager |  | X
Client
|  | Client Prime |  | X
|  | DEM Prime |  | X
|  | Process Prime |  | X
|  | Indirect |  |  |  | Indirect estimate checklist:
| Subject Matter Experts from Client Organizations |  |  | X
| Subject Matter Experts from other IS depts. |  |  | X
| Employee Advisory Committees |  |  | X
| Client Advisory Committee |  |  | X
| Vendor Management |  |  | X
Userid Administration
| Data Standards Forum |  |  | X
| Data Management |  |  | X
| Architecture |  |  | X
| Core Baan Program interface organization |  |  | X
| Integration Testing |  |  | X
| Item |  | estimated | not estimated * |  | Project support estimate checklist:
| Database Administration |  |  | X
| Resource Management |  |  | X
| Verification and Validation |  |  | X
| Configuration Management |  |  | X
| Quality Assurance/Facilitation |  |  | X
| Electronic Data Interchange |  |  | X
| New Product Introduction |  |  | X
| Product Management |  |  | X
| Core Baan Program Interfaces |  |  | X
| Networking and Computing |  |  | X
| Processing Services |  |  | X
| Finance |  |  | X
| Application Modifications - vendor |  |  | X
| Third Party Suppliers(e.g. EPIC, Baan, Origin) |  |  | X
| IS Skills Development |  |  | X
| 3rd party warranty support vs contracted support. |  |  | X
| computer operations support |  |  | X
| outsourced support |  |  | X
| Level-1/Level-2 support |  |  | X

## (3) Hardware
Custos de hardware |  |  |  |  | 0
Sample table
| Server Hardware … | Preço por unidade | Quantidade | Total |  | Outras informações
| para desenvolvimento |  |  | 0
| para testes |  |  | 0
| para treinamento |  |  | 0
| para produção |  |  | 0
| Total (Server) |  |  | 0
| Desktop Hardware … | Preço por unidade | Quantidade | Total |  | Outras informações
| para desenvolvimento |  |  | 0
| para testes |  |  | 0
| para treinamento |  |  | 0
| para produção |  |  | 0
| Total (Desktop) |  |  | 0
0
Hardware estimate checklist:
| Item |  | estimated | not estimated *
| Cpu Hardware |  |  | X
| Servers |  |  | X
| Modem |  |  | X
| Extraordinary power supply |  |  | X
needs
| Backup Systems |  |  | X
| Disaster Recovery Systems |  |  | X
| Additional Memory |  |  | X
| Processing Services |  |  | X
| Disk Storage |  |  | X
| Tape Backup |  |  | X
| UPS |  |  | X
| Switching devices |  |  | X
| Routers |  |  | X
| Racks |  |  | X
| Local taxes |  |  | X
| shipping, handling(delivery) |  |  | X
| installation |  |  | X

## (4) Software
Total "Software Cost estimate" |  |  |  | 0
Sample table
| Server Software … | Preço por unidade | Quantidade | Total | Outras informações
| para desenvolvimento |  |  | 0
| para testes |  |  | 0
| para treinamento |  |  | 0
| para produção |  |  | 0
| Total (Servidor) |  |  | 0
| Desktop Software … | Preço por unidade | Quantidade | Total | Outras informações
| para desenvolvimento |  |  | 0
| para testes |  |  | 0
| para treinamento |  |  | 0
| para produção |  |  | 0
| Total (Desktop) |  |  | 0
0
Software estimate checklist:
| Item | estimated | not estimated *
| Application Licenses |  | X
| Security (Nortel.Access) |  | X
| RDBMS Licences |  | X
| Project specific Software tools |  | X
| Application Mods - vendor |  | X
| Any costs that this project must bear |  | X
to decommission Legacy Systems
| Archiving |  | X
| Communication SW (e.g. MQ Series) |  | X
| Userid Administration |  | X
| also include: |  | X
| The number of licenses |  | X
| Any installation costs |  | X
| S&H costs |  | X
| support costs |  | X

## (5) Network HW-SW
Total "Network Cost estimate" |  |  |  | 0
| Rede servidor … | Preço por unidade | Quantidade | Total |  | Outras informações
| para desenvolvimento |  |  | 0
| para testes |  |  | 0
| para treinamento |  |  | 0
| para produção |  |  | 0
| Total (Servidor) |  |  | 0
| Rede desktop | Preço por unidade | Quantidade | Total |  | Outras informações
| para desenvolvimento |  |  | 0
| para testes |  |  | 0
| para treinamento |  |  | 0
| para produção |  |  | 0
| Total (Servidor) |  |  | 0
0
Network estimate checklist:
| Item |  |  |  | estimated | not estimated *
| LAN |  |  |  |  | X
| WAN |  |  |  |  | X
| Routers |  |  |  |  | X
| Dial-up Lines |  |  |  |  | X
| Dedicated lines |  |  |  |  | X
| Satellite |  |  |  |  | X
| Ports |  |  |  |  | X
| Phones |  |  |  |  | X
| Controllers |  |  |  |  | X
| Switches |  |  |  |  | X
| SW licenses |  |  |  |  | X
| Setting up Access (e.g. Secure ID) |  |  |  |  | X
| Other security … Firewall, etc. |  |  |  |  | X
Processing Services
| (estimate 15-20% of the hardware costs per annum) |  |  |  |  | X

## (6) Custos administrativos
Custos administrativos para estimar |  |  | 0
Sample table
| Itens administrativos |  |  | Observações
Viagens
Refeições
etc.
0
"Admin costs not in Overhead" estimate checklist:
| Item |  | estimated | not estimated *
| Conferences |  |  | X
| Internal or external |  |  | X
| Face to Face meetings |  |  | X
| Audio/Video teleconferences |  |  | X
| Internal Audit |  |  | X
Quality Assurance
| extraordinary Communications |  |  | X
| Printing (e.g. manuals, training material) |  |  | X
| Project Website development and maintenance |  |  | X
| Use of Learning Institute |  |  | X
| Administration support |  |  | X
| Marketing |  |  | X
| Electrical work |  |  | X
| network connections |  |  | X
| lighting |  |  | X
| furniture |  |  | X
| special Air conditioning |  |  | X
| Team recognition/celebration |  |  | X

## Risk & Change
Replace this page with your project risk chart
The following is provided as a basic template that may be used in the
analysis and documentation of project risks:
|  | Probability of Occurrence |  |  | Impact |  |  | Planned Action
Risk number | Activity/Requirement | low | medium | high | low | medium | high | no action | type of action | Risk weight *